## About
ABOUT THIS GANTT CHART
Visualize and track your projects using this Gantt chart template. To start, enter the tasks you're working on in the Milestone Description section and then enter details for each task. The data will automatically update and it’s easy to insert new tasks or use the scrollbar to scroll through the timeline.
• Use Progress to add how much of the project you finished by adding a percentage number. • Add the day you started your project in the Start Date. • Finish your calculations by filling in the number of days you need to complete your project in the No. of Days field.

## Light
PROJECT TITLE
Company name |  |  |  |  | Legend: | On track |  |  |  |  | Low risk |  |  |  |  | Med risk |  |  |  |  | High risk |  |  |  |  | Unassigned
Project lead
Project Start Date: | 2021-04-27 |  |  |  |  | April | [6 empty] | May | [27 empty] | June
Scrolling Increment: | 1 | time axis 2021-04-28 to 2021-06-22
Milestone description | Category | Assigned to | Progress | Start | Days | time axis 2021-04-28 to 2021-06-22
TITLE 1
Task 1 | Goal | Name | 25% | 2021-04-27 | 3 | 2021-04-28: 2; 2021-04-29: 2
Task 2 | Milestone |  |  | 2021-05-02 | 1 | bar: 2021-05-02
Task 3 | Low Risk |  | 50% | 2021-04-24 | 10
Task 4 | Milestone |  |  | 2021-05-17 | 1 | bar: 2021-05-17
Task 5 | Med Risk |  | 10% | 2021-05-03 | 6
TITLE 2
Task 1 | High Risk |  | 60% | 2021-05-03 | 13
Task 2 | On Track |  | 50% | 2021-05-05 | 9
Task 3 | Low Risk |  | 33% | 2021-05-10 | 11
Task 4 | Milestone |  |  | 2021-05-12 | 1 | bar: 2021-05-12
Task 5 |  |  |  | 2021-05-13 | 24
TITLE 3
Task 1 | On Track |  |  | 2021-05-12 | 4
Task 2 | Med Risk |  |  | 2021-05-15 | 14
Task 3 | On Track |  |  | 2021-05-30 | 6
Task 4 | Goal |  |  | 2021-06-03 | 3 | 2021-06-03: 2; 2021-06-04: 2; 2021-06-05: 2
Task 5 | Low Risk |  |  | 2021-05-03 | 19
TITLE 4
Task 1 |  |  |  | 2021-06-06 | 15
Task 2 |  |  |  | 2021-06-20 | 5
Task 3 | Milestone |  |  | 2021-08-01 | 1
Task 4
Task 5
To add more data, Insert new rows ABOVE this one

## Dark
PROJECT TITLE
Company name |  |  |  |  | Legend: | On track |  |  |  |  | Low risk |  |  |  |  | Med risk |  |  |  |  | High risk |  |  |  |  | Unassigned
Project lead
Project Start Date: | 2021-04-27 |  |  |  |  | April | [6 empty] | May | [27 empty] | June
Scrolling Increment: | 1 | time axis 2021-04-28 to 2021-06-22
Milestone description | Category | Assigned to | Progress | Start | Days | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T
TITLE 1
Task 1 | Goal | Name | 25% | 2021-04-27 | 3 | W: 2; T: 2
Task 2 | Milestone |  |  | 2021-05-02 | 1 | bar: S
Task 3 | Low Risk |  | 50% | 2021-04-24 | 10
Task 4 | Milestone |  |  | 2021-05-17 | 1 | bar: M
Task 5 | Med Risk |  | 10% | 2021-05-03 | 6
TITLE 2
Task 1 | High Risk |  | 60% | 2021-05-03 | 13
Task 2 | On Track |  | 50% | 2021-05-05 | 9
Task 3 | Low Risk |  | 33% | 2021-05-10 | 11
Task 4 | Milestone |  |  | 2021-05-12 | 1 | bar: W
Task 5 |  |  |  | 2021-05-13 | 24
TITLE 3
Task 1 | On Track |  |  | 2021-05-12 | 4
Task 2 | Med Risk |  |  | 2021-05-15 | 14
Task 3 | On Track |  |  | 2021-05-30 | 6
Task 4 | Goal |  |  | 2021-06-03 | 3 | T: 2; F: 2; S: 2
Task 5 | Low Risk |  |  | 2021-05-03 | 19
TITLE 4
Task 1 |  |  |  | 2021-06-06 | 15
Task 2 |  |  |  | 2021-06-20 | 5
Task 3 | Milestone |  |  | 2021-08-01 | 1
Task 4
Task 5
To add more data, Insert new rows ABOVE this one

## Color
Splendid
Daniel Akoto |  |  |  | Legend: |  | On track |  |  |  |  | Low risk |  |  |  |  | Med risk |  |  |  |  | High risk |  |  |  |  | Unassigned
Individual Project
Project Start Date: | 2021-04-27 |  |  |  |  | March | [13 empty] | April | [27 empty] | May
Scrolling Increment: | 0 | time axis 2021-03-23 to 2021-05-17
Milestone description | Category | Progress | Start | Days | Date Completed & Reason | time axis 2021-03-23 to 2021-05-17
Planning
Design Review | Milestone | 100% | 2021-03-23 | 18 | 4/1/2021, The Design was altered later in the project during Design Review | bar: 2021-03-23 to 2021-04-09
Tool Selection | Milestone | 100% | 2021-03-23 | 18 | 4/1/2021, New tools were added into the list. | bar: 2021-03-23 to 2021-04-09
SPMP | Milestone | 100% | 2021-03-23 | 18 | 2021-04-01 | bar: 2021-03-23 to 2021-04-09
PROPOSAL | Milestone | 100% | 2021-03-23 | 1 | 2021-04-01 | bar: 2021-03-23
Implementation
Set Up Work Environment | Low Risk | 100% | 2021-04-03 | 1 | 4/4/2021, The dates of all the Implementation tasks were moved forward days.
Reviewing Design Process | Low Risk | 100% | 2021-04-03 | 1 | 2021-04-03
Researching Color Schemes and Logo | Low Risk | 100% | 2021-04-03 | 2 | 2021-04-05
Designing Logo and Picking Colors | Low Risk | 100% | 2021-04-03 | 3 | 4/8/2021, Getting a color scheme was difficult because I changed the schem multiple times
Implementing Design Process into HTML, CSS, JS | Med Risk | 100% | 2021-04-04 | 9 | 2021-04-15
Debugging | High Risk | 100% | 2021-04-04 | 9 | 4/22/2021, I completed most of the debugging in while working on multiple parts.
Implementing songs and Lists | Med Risk | 100% | 2021-04-04 | 13 | 4/10/2021, The songs did not take as long as I thougt it woul take.
Implementing Spotify, Apple Music &YouTube | Med Risk | 100% | 2021-04-05 | 7 | 4/22/2021, The embeeding process only too a few minutes, spotify makes it easy.
Frame CSS for Spotify, Apple music & YouTube | Med Risk | 100% | 2021-04-08 | 7 | 4/14/2021,
Finalizing Design and Hosting | High Risk | 100% | 2021-04-09 | 9 | 4/26/2021, I began hosting the site a lot earlier than predicted. ( 4/1/2021)
To add more data, Insert new rows ABOVE this one